## Dashboard
CAPA METRICS DASHBOARD
SUMMARY METRICS
Total CAPAs | 1
Open CAPAs | 1
Closed CAPAs | 0
Overdue CAPAs | 1
Avg Days to Close | 0
% Closed On Time | 0%
BREAKDOWN BY STATUS |  | BREAKDOWN BY TYPE
Open | 0 | Corrective | 1
In Progress | 1 | Preventive | 0
Awaiting Verification | 0 | Both | 0
Closed | 0
Cancelled | 0

## CAPA Tracker
CORRECTIVE AND PREVENTIVE ACTION (CAPA) TRACKER
AS9100 / ISO 9001 Compliant - Nonconformance Management System
Instructions: Blue text = User input required ¦ Black text = Auto-calculated ¦ Status updates trigger workflow
CAPA ID | Date Opened | Source | Type | Nonconformance Description | Root Cause | Containment Action | Corrective Action | Preventive Action | Responsible Person | Target Date | Completion Date | Status | Days Open | Overdue? | Verification Status
CAPA-0001 | 2025-12-15 | Internal Audit | Corrective | Control plan missing critical characteristic for bearing assembly process | 8D analysis revealed inadequate process FMEA - critical feature severity rating was incorrect | 100% inspection implemented on lot XYZ-789 pending PFMEA revision | Revise PFMEA for bearing assembly (Doc# PFMEA-BA-001 Rev C). Update control plan per AIAG guidelines. | Train quality engineers on PFMEA severity rating criteria. Add PFMEA review to new product introduction checklist. | J. Smith (Quality Mgr) | 2026-01-31 |  | In Progress | 55 | YES | Pending
Formulas:
Days Open = IF(AND([Date Opened]<>"",[Completion Date]=""),TODAY()-[Date Opened],IF(AND([Date Opened]<>"",[Completion Date]<>""),[Completion Date]-[Date Opened],""))
Overdue? = IF(AND([Target Date]<>"",[Completion Date]="",TODAY()>[Target Date]),"YES",IF(AND([Target Date]<>"",[Completion Date]<>"",[Completion Date]>[Target Date]),"WAS LATE",""))

## Validation Lists (hidden)
Internal Audit | Corrective | Open | Pending
External Audit | Preventive | In Progress | Verified Effective
Customer Complaint | Both | Awaiting Verification | Not Effective - Reopen
Supplier Issue |  | Closed | N/A
Production Nonconformance |  | Cancelled
Management Review
Employee Suggestion
Regulatory Finding
Risk Assessment
Other