## DFMEA
DESIGN FAILURE MODE AND EFFECTS ANALYSIS (DFMEA)
AIAG-4 Compliant ¦ Risk Priority Number (RPN) Methodology
Item/Product: | Battery Pack Assembly |  | DFMEA Number: | DFMEA-2025-001 |  | Prepared By: | Engineering Team |  | Date: | 2025-02-07 |  | Revision: | Rev A
FAILURE MODE ANALYSIS |  |  | INITIAL ASSESSMENT (Before Actions) | [6 empty] | ACTIONS |  |  | REVISED ASSESSMENT (After Actions)
Item/ Function | Potential Failure Mode | Potential Effect(s) of Failure | SEV | Class | Potential Cause(s) of Failure | OCC | Current Design Controls | DET | RPN | Recommended Action(s) | Responsibility & Target Date | Action Taken | SEV | OCC | DET | RPN
Battery Cell Containment | Cell rupture during thermal runaway | Fire, injury to user, property damage | 10 | Critical | Internal short circuit from manufacturing defect | 4 | Incoming CT scan, pressure relief valve | 6 | 240 | Add thermal barrier between cells, implement abuse testing per UL 2580 | Design Team / 2025-03-15 | Thermal barrier added, abuse testing passed | 10 | 2 | 4 | 80
Battery Management System | BMS fails to detect overcharge | Cell degradation, reduced capacity, potential fire | 9 | Critical | Software bug in voltage monitoring algorithm | 3 | Software FMEA, code reviews, bench testing | 5 | 135 | Implement redundant voltage sensing, add watchdog timer | Electrical Team / 2025-03-30

## Rating Criteria
DFMEA RATING CRITERIA - AIAG REFERENCE
SEVERITY (SEV) - Effect on Customer
Rating | Criteria | Description
10 | Hazardous without warning | Very high severity - Safety related, non-compliance with regulations
9 | Hazardous with warning | High severity - Safety related with warning
8 | Very High | Product inoperable, loss of primary function
7 | High | Product performance severely degraded
6 | Moderate | Product performance degraded, comfort/convenience affected
5 | Low | Product performance slightly degraded
4 | Very Low | Fit & finish/squeak & rattle item does not conform
3 | Minor | Fit & finish/squeak & rattle item barely noticeable
2 | Very Minor | Fit & finish/squeak & rattle item noticed by discriminating customers
1 | None | No effect
OCCURRENCE (OCC) - Likelihood of Cause
Rating | Criteria | Probability
10 | Almost Certain | ≥ 1 in 2
9 | Very High | 1 in 3
8 | High | 1 in 8
7 | Moderately High | 1 in 20
6 | Moderate | 1 in 80
5 | Low | 1 in 400
4 | Moderately Low | 1 in 2,000
3 | Remote | 1 in 15,000
2 | Very Remote | 1 in 150,000
1 | Nearly Impossible | < 1 in 1,500,000
DETECTION (DET) - Likelihood of Detection Before Release
Rating | Likelihood | Description
10 | Almost Impossible | Design control will not and/or cannot detect
9 | Very Remote | Very remote chance detection will occur
8 | Remote | Remote chance detection will occur
7 | Very Low | Very low chance detection will occur
6 | Low | Low chance detection will occur
5 | Moderate | Moderate chance detection will occur
4 | Moderately High | Moderately high chance detection will occur
3 | High | High chance detection will occur
2 | Very High | Very high chance detection will occur
1 | Almost Certain | Design control will almost certainly detect
RPN INTERPRETATION & ACTION PRIORITY
Condition | Priority | Action
RPN > 200 | Critical | Immediate action required
RPN 100-200 | High Priority | Action required before production
RPN 40-99 | Medium Priority | Action recommended
RPN < 40 | Low Priority | Monitor, action optional
SEV = 9 or 10 | Critical Safety | Action required regardless of RPN